## Control Sheet
Scenario Id | Description | Expected Result | Assigned To | Reviewed by | Weekday - 1 | [6 empty] | Weekday - 2 | [6 empty] | Weekday - 3 | [6 empty] | Weekday - 4 | [6 empty] | Start Date | End Date
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Login Page |  | Prasasth | Rajesh S | [28 empty] | 16-01-2020 | 17-01-2020
2 | My Team Page |  | Prasasth | Rajesh S | [28 empty] | 16-01-2020 | 17-01-2020
3 | Points Page |  | Prasasth | Rajesh S | [28 empty] | 16-01-2020 | 17-01-2020
4 | Transfers Page |  | Prasasth | Rajesh S | [28 empty] | 16-01-2020 | 17-01-2020
5 | Leagues Page |  | Prasasth | Rajesh S | [28 empty] | 16-01-2020 | 17-01-2020

## Test Scenario
Scenario Id | Sub Scenario Id | Description | Expected Result
1 |  | Login Page
| 1.1 | Authentication | Login details accepted
| 1.1.1 | Login Details Verification | User email and password should be verified
| 1.1.2 | User Sign In | User Should be allowed to Login
| 1.2 | User Registration | User should be allowed to create new account
| 1.2.1 | Email Verification | User email should be verified and linked
| 1.3 | Forgot Password | User should be allowed to request to change password via email link
| 1.3.1 | Redirect Link | User should be able to set new password upon clicking the link
2 |  | My Team Page
| 2.1 | Changes to Team | User should be able to make changes to team as per the given options
| 2.1.1 | Player in playing XI | User should be able to substitute player with player on bench(same position) or choose between making captain or vice captain or view information about the player
| 2.1.2 | Player on bench | User should be able to substitute player with playerin playing XI(same position) or view information about the player
| 2.1.3 | Saving changes | User should be able to save changes made to team
| 2.2 | Using Chips | User should be able to select chip(one use only) and activate it for the current gameweek
| 2.2.1 | Bench Boost | User should be able to activate Bench Boost for the current gameweek
| 2.2.2 | Triple Captain | User should be able to activate Triple Captain for the current gameweek
| 2.2.3 | Free Hit | User should be able to activate Free Hit for the current gameweek
| 2.3 | Switching views | User should be able to switch between pitch view and list view
| 2.4 | Fixtures list | User should be able to view fixtures of upcoming gameweek and be able to switch between gameweeks
3 |  | Points Page
| 3.1 | View points | User should be able to view points for current/most recent game week and older gameweeks also
| 3.1.1 | View player points | User should be able to view points of selected player for current/most recent game week and older gameweeks also
| 3.2 | View Dream Team | User should be able to view Dream Team of same gameweek
| 3.3 | Switching views | User should be able to switch between pitch view and list view
| 3.4 | Fixtures list | User should be able to view fixtures and results of ongoing/completed gameweek and be able to switch between gameweeks
4 |  | Transfers Page
| 4.1 | Transfer Buttons | User should be able to access options via these buttons
| 4.1.1 | Auto Pick | User should have their team autofilled based on the best permutation available
| 4.1.2 | Reset | User should be able to undo all changes made before saving
| 4.1.3 | Play Wildcard | User should be able to activate wildcard after making changes (one time use)
| 4.1.4 | Make Transfers | User should be able to confirm changes made and redirect to my team page
| 4.2 | Transferring players | User should be able to choose which player to transfer out
| 4.2.1 | Selecting player in team | User should be able to choose whether to remove or replace player or view info
| 4.2.2 | Selecting empty slot in team | User should be able to choose whether to add player or restore removed player
| 4.3 | Player Selection from List | User should be able to select which player to add to team from the list available
| 4.3.1 | Filters | User should be able to filter list via the given options
| 4.3.2 | Selecting player name | User should be able to choose whether to add player to team or view info
| 4.3.3 | View Information | User should be able to view information of player selected
| 4.3.4 | List page navigator | User should be able to navigate between pages of players list
| 4.4 | Exceptions | User should be prompted upon performing a task against the rules
| 4.4.1 | Too many players of same position | User should not be allowed to add player of maxed out position and prompted the same
| 4.4.2 | Too many players of same team | User should be prompted upon adding more than 3 players from the same club
| 4.4.3 | Budget exceeded | User should be prompted upon adding a player whose cost exceeds the players remaining budget
| 4.4.4 | Player already in team | User should not be allowed to select player that is already present in team from the list
| 4.5 | Switching views | User should be able to switch between pitch view and list view
| 4.6 | Fixtures list | User should be able to view fixtures of upcoming gameweek and be able to switch between gameweeks
5 |  | Leagues Page
| 5.1 | New League | User should be given options to create, join or renew leagues
| 5.2 | Existing League | User should be able to view their standings in all leagues they are members of
| 5.2.1 | League Member | User should be able to choose whether to leave league or view standings
| 5.2.2 | League Admin | User should be able to choose whether to view standings, invite friends or administer league
| 5.3 | Selected League | User should be able to view expanded standings of selected league
| 5.3.1 | View Team | User should be able to view team of other members of selected league
| 5.3.2 | Filters | User should be able to filter standings by phase or month
| 5.4 | League Administration | User should be able to perform changes on league if they are the admin
| 5.4.1 | League Code | User should be able to view or regenarate league code
| 5.4.2 | League Details | User should be able to change league name, scoring and privacy setttings
| 5.4.3 | League Delete | User should be able to delete league

## Test Script
Scenario Id | Sub Scenario Id | Script ID/Step | Description | Expected Result
1 |  |  | Login Page
| 1.1 |  | Authentication | Login details accepted
|  | 1 | Enter User email | User email accepted and verified
|  | 2 | Select password entry box | Password ready to be accepted
| 1.1.1 |  | Login Details Verification | User name and password should be verified
|  | 1 | Enter password | Password verified
| 1.1.2 |  | User Sign In | User Should be allowed to Login
|  | 1 | Click Login | User logged in and redirected to home page
| 1.2 |  | User Registration | User should be allowed to create new account
|  | 1 | Enter user email id | User email id verified and accepted
|  | 2 | Enter password/ confirm password | Password accepted and verified
|  | 3 | Click register | Redirect to select team page
| 1.2.1 |  | Email Verification | User email should be verified and linked
|  | 1 | Click confirm email id | User sent confirmation link to registered email
|  | 2 | Click link in registered email id | User redirected to homepage
| 1.3 |  | Forgot Login details | User should be allowed to request forgotten login details via email
|  | 1 | Click forgot password | User redirected to forgot password popup
|  | 2 | Enter username | Username verified
|  | 3 | Click change password | Change password link sent to email id
| 1.3.1 |  | Redirect Link | User should be able to set new details upon clicking the link
|  | 1 | Click link in registered email id | User redirected to change password page
|  | 2 | Enter and confirm new password | New password verified and password successfully changed
2 |  |  | My Team Page
| 2.1 |  | Changes to Team | User should be able to make changes to team as per the given options
|  | 1 | Click on My Team Tab | User redirected to My Team page
| 2.1.1 |  | Player in playing XI | User should be able to substitute player with player on bench(same position) or choose between making captain or vice captain or view information about the player
|  | 1 | Click on any player | User prompted with options
|  | 2 | Choose action view info | User prompted with popup of player information
|  | 3 | Choose substitute | Available bench players highlighted and swapped with player ince chosen
|  | 4 | Set Vice Captain/Vice Captain (Optional) | User allowed to set one player in playing XI as captain and one as vice captain
| 2.1.2 |  | Player on bench | User should be able to substitute player with playerin playing XI(same position) or view information about the player
|  | 1 | Click on any player | User prompted with options
|  | 2 | Choose action | User prompted with popup of player information
|  | 3 | Choose substitute | Available bench players highlighted and swapped with player ince chosen
| 2.1.3 |  | Saving changes | User should be able to save changes made to team
|  | 1 | Click save your team | User team changes saved and page is reloaded with new team structure
| 2.2 |  | Using Chips (Only one at a time) | User should be able to select chip(one use only) and activate it for the current gameweek
|  | 1 | Select chip from available options | Selected chip is activated upon start of next gameweek
| 2.2.1 |  | Bench Boost | User should be able to activate Bench Boost Chip
|  | 1 | Click Bench Boost | Bench Boost selected and activated upon start of next gameweek
|  | 2 | Click Cancel | Bench Boost cancelled (Can only be done before activation at start of next gameweek)
| 2.2.2 |  | Triple Captain | User should be able to activate Triple Captain Chip
|  | 1 | Click Triple Captain | Triple Captain selected and activated upon start of next gameweek
|  | 2 | Click Cancel | Triple Captain cancelled (Can only be done before activation at start of next gameweek)
| 2.2.3 |  | Free Hit | User should be able to activate Free Hit Chip
|  | 1 | Click Free Hit | Free Hit selected and activated upon start of next gameweek
|  | 2 | Click Cancel | Free Hit cancelled (Can only be done before activation at start of next gameweek)
| 2.3 |  | Switching views | User should be able to switch between pitch view and list view
|  | 1 | Click List view | List View loaded
|  | 2 | Click pitch view | Pitch View loaded
| 2.4 |  | Fixtures list | User should be able to view fixtures of upcoming gameweek and be able to switch between gameweeks
|  | 1 | Click next gameweek | Next gameweek fixtures loaded
|  | 2 | Click previous gameweek | Previous gameweek fixtures loaded
3 |  |  | Points Page
| 3.1 |  | View points | User should be able to view points for current/most recent game week and older gameweeks also
|  | 1 | Click Points tab | Points Page loaded for current/ongoing gameweek
| 3.1.1 |  | View player points | User should be able to view points of selected player for current/most recent game week and older gameweeks also
|  | 1 | Click on any player | Popup with current/ongoing gameweek points breakdown launched
|  | 2 | Click View Info | Player Information is displayed
| 3.2 |  | View Dream Team | User should be able to view Dream Team of same gameweek
|  | 1 | Click Dream Team | User redirected to Dream Team of current/ongoing gameweek
| 3.3 |  | Switching views | User should be able to switch between pitch view and list view
|  | 1 | Click List view | List View loaded
|  | 2 | Click pitch view | Pitch View loaded
| 3.4 |  | Fixtures list | User should be able to view fixtures and results of ongoing/completed gameweek and be able to switch between gameweeks
|  | 1 | Click next gameweek | Next gameweek fixtures loaded
|  | 2 | Click previous gameweek | Previous gameweek fixtures loaded
4 |  |  | Transfers Page
| 4.1 |  | Transfer Buttons | User should be able to access options via these buttons
|  | 1 | Choose button to click on | Said action completed upon clicking of button
| 4.1.1 |  | Auto Pick | User should have their team autofilled based on the best permutation available
|  | 1 | Click Auto Pick button | Team autofilled based on best permutation
| 4.1.2 |  | Reset | User should be able to undo all changes made before saving
|  | 1 | Click reset button | All unsaved changes are reset to default
| 4.1.3 |  | Play Wildcard | User should be able to activate wildcard after making changes (one time use)
|  | 1 | Click Play Wildcard Button | Wildcard activated
| 4.1.4 |  | Make Transfers | User should be able to confirm changes made and redirect to my team page
|  | 1 | Click Make Transfers | Popup appears with list of changes made and confrimation is asked
|  | 2 | Click Confirm | Transfers confirmed and my team page loaded
| 4.2 |  | Transferring players | User should be able to choose which player to transfer out
|  | 1 | Select which player to remove and add | User can choose to add or remove players
| 4.2.1 |  | Selecting player in team | User should be able to choose whether to remove or replace player or view info
|  | 1 | Click on player | Popup appears with options to remove, replace or view info
|  | 2 | Click on remove | Player is removed and slot is now empty
| 4.2.2 |  | Selecting empty slot in team | User should be able to choose whether to add player or restore removed player
|  | 1 | Click on empty slot | Popup appears with options to add player or restore the original player
|  | 2 | Click on add player | Player List reloads with available players from that position
| 4.3 |  | Player Selection from List | User should be able to select which player to add to team from the list available
|  | 1 | Click on player name | Popup appears with options to add player to team or view info
|  | 2 | Click on add player | Player added to team in any empty slot in the same position
| 4.3.1 |  | Filters | User should be able to filter list via the given options
|  | 1 | Select filters | Player List reloads and filtered list is shown
| 4.3.2 |  | Selecting player name | User should be able to choose whether to add player to team or view info
|  | 1 | Click on player name | Popup appears with options to add player to team or view info
|  | 2 | Click on add player | Player added to team in any empty slot in the same position
| 4.3.3 |  | View Information | User should be able to view information of player selected
|  | 1 | Click View Information | Player information is displayed in a popup
| 4.3.4 |  | List page navigator | User should be able to navigate between pages of players list
|  | 1 | Next Page | Next page in list loaded
|  | 2 | Previous Page | Previous page in list loaded
| 4.4 |  | Exceptions | User should be prompted upon performing a task against the rules
| 4.4.1 |  | Too many players of same position | User should not be allowed to add player of maxed out position and prompted the same
|  | 1 | Add player of certain position to team where all positions are filled up | Get prompt saying you can't add more than X no. of players for the selected position
|  | 2 | Validate exception | Make transfers button disabled
| 4.4.2 |  | Too many players of same team | User should be prompted upon adding more than 3 players from the same club
|  | 1 | Add a player to team where 3 other players of same club already exist | Player added and get prompt saying you have more than 3 players of same club. Make transfers button is disabled
|  | 2 | Validate exception | Make transfers button disabled
| 4.4.3 |  | Budget exceeded | User should be prompted upon adding a player whose cost exceeds the players remaining budget
|  | 1 | Add a player whose price exceeds the amount left in bank | Player added; Amount in bank shows negative value in red and make transfers button is disabled
|  | 2 | Validate exception | Make transfers button disabled
| 4.4.4 |  | Player already in team | User should not be allowed to select player that is already present in team from the list
|  | 1 | Click add player | Players already in team are disabled and cannot be added
|  | 2 | Validate exception | Make transfers button disabled
| 4.5 |  | Switching views | User should be able to switch between pitch view and list view
|  | 1 | Click List view | List View loaded
|  | 2 | Click pitch view | Pitch View loaded
| 4.6 |  | Fixtures list | User should be able to view fixtures of upcoming gameweek and be able to switch between gameweeks
|  | 1 | Click next gameweek | Next gameweek fixtures loaded
|  | 2 | Click previous gameweek | Previous gameweek fixtures loaded
5 |  |  | Leagues Page
| 5.1 |  | New League | User should be given options to create, join or renew leagues
|  | 1 | Click create/join new league | Redirect to page with options to create new league or join new league
| 5.2 |  | Existing League | User should be able to view their standings in all leagues they are members of
|  | 1 | Browse my leagues | Display standings in each league in which the User is a member
| 5.2.1 |  | League Member | User should be able to choose whether to leave league or view standings
|  | 1 | Click on gear icon next to league with different admin | Popup appears with options to view league standings or leave the league
| 5.2.2 |  | League Admin | User should be able to choose whether to view standings, invite friends or administer league
|  | 1 | Click on gear icon next to league where Admin is the User | Popup appears with options to view league standings or invite friends or administer the league
| 5.3 |  | Selected League | User should be able to view expanded standings of selected league
|  | 1 | Click on league name | Redirected to new page with league standings (detailed)
| 5.3.1 |  | View Team | User should be able to view team of other members of selected league
|  | 1 | Click on any team name in any league | Redirected to point page of selected team
| 5.3.2 |  | Filters | User should be able to filter standings by phase or month
|  | 1 | Choose filters for standings | Standings with filters applied are shown
| 5.4 |  | League Administration | User should be able to perform changes on league if they are the admin
|  | 1 | Click on administer league on the popup of gear icon next to league where User is admin | League Administration page is opened
| 5.4.1 |  | League Code | User should be able to view or regenarate league code
|  | 1 | Click regenerate | New league code generated
| 5.4.2 |  | League Details | User should be able to change league name, scoring and privacy setttings
|  | 1 | Enter new details | League details changed
| 5.4.3 |  | League Delete | User should be able to delete league
|  | 1 | Click Delete League | League Deleted

## Test Script Execution
Scenario Id | Sub Scenario Id | Script ID/Step | Description | Expected Result | Actual Result | Conclusion
1 |  |  | Login Page
| 1.1 |  | Authentication | Login details accepted
|  | 1 | Enter User email | User email accepted and verified | User email accepted and verified | PASS
|  | 2 | Select password entry box | Password ready to be accepted | Password ready to be accepted | PASS
| 1.1.1 |  | Login Details Verification | User name and password should be verified
|  | 1 | Enter password | Password verified | Password verified | PASS
| 1.1.2 |  | User Sign In | User Should be allowed to Login
|  | 1 | Click Login | User logged in and redirected to home page | User not logged in and login page is reloaded | FAIL
| 1.2 |  | User Registration | User should be allowed to create new account
|  | 1 | Enter user email id | User email id verified and accepted | User email id verified and accepted | PASS
|  | 2 | Enter password/ confirm password | Password accepted and verified | Password accepted and verified | PASS
|  | 3 | Click register | Redirect to select team page | Redirect to select team page | PASS
| 1.2.1 |  | Email Verification | User email should be verified and linked
|  | 1 | Click confirm email id | User sent confirmation link to registered email | User sent confirmation link to registered email | PASS
|  | 2 | Click link in registered email id | User redirected to homepage | User redirected to homepage | PASS
| 1.3 |  | Forgot Login details | User should be allowed to request forgotten login details via email
|  | 1 | Click forgot password | User redirected to forgot password popup | User redirected to forgot password popup | PASS
|  | 2 | Enter username | Username verified | Username verified | PASS
|  | 3 | Click change password | Change password link sent to email id | Change password link sent to email id | PASS
| 1.3.1 |  | Redirect Link | User should be able to set new details upon clicking the link
|  | 1 | Click link in registered email id | User redirected to change password page | User redirected to change password page | PASS
|  | 2 | Enter and confirm new password | New password verified and password successfully changed | New password verified and password successfully changed | PASS
2 |  |  | My Team Page
| 2.1 |  | Changes to Team | User should be able to make changes to team as per the given options
|  | 1 | Click on My Team Tab | User redirected to My Team page | User redirected to My Team page | PASS
| 2.1.1 |  | Player in playing XI | User should be able to substitute player with player on bench(same position) or choose between making captain or vice captain or view information about the player
|  | 1 | Click on any player | User prompted with options | User prompted with options | PASS
|  | 2 | Choose action view info | User prompted with popup of player information | User prompted with popup of player information | PASS
|  | 3 | Choose substitute | Available bench players highlighted and swapped with player ince chosen | Available bench players highlighted and swapped with player ince chosen | PASS
|  | 4 | Set Vice Captain/Vice Captain | User allowed to set one player in playing XI as captain and one as vice captain | User not allowed to set one player in playing XI as captain and one as vice captain | FAIL
| 2.1.2 |  | Player on bench | User should be able to substitute player with playerin playing XI(same position) or view information about the player
|  | 1 | Click on any player | User prompted with options | User prompted with options | PASS
|  | 2 | Choose action | User prompted with popup of player information | User prompted with popup of player information | PASS
|  | 3 | Choose substitute | Available bench players highlighted and swapped with player ince chosen | Available bench players highlighted and swapped with player ince chosen | PASS
| 2.1.3 |  | Saving changes | User should be able to save changes made to team
|  | 1 | Click save your team | User team changes saved and page is reloaded with new team structure | User team changes saved and page is reloaded with new team structure | PASS
| 2.2 |  | Using Chips (Only one at a time) | User should be able to select chip(one use only) and activate it for the current gameweek
|  | 1 | Select chip from available options | Selected chip is activated upon start of next gameweek | Selected chip is activated upon start of next gameweek | PASS
| 2.2.1 |  | Bench Boost | User should be able to activate Bench Boost Chip
|  | 1 | Click Bench Boost | Bench Boost selected and activated upon start of next gameweek | Bench Boost selected and activated upon start of next gameweek | PASS
|  | 2 | Click Cancel | Bench Boost cancelled (Can only be done before activation at start of next gameweek) | Bench Boost cancelled (Can only be done before activation at start of next gameweek) | PASS
| 2.2.2 |  | Triple Captain | User should be able to activate Triple Captain Chip
|  | 1 | Click Triple Captain | Triple Captain selected and activated upon start of next gameweek | Triple Captain selected and activated upon start of next gameweek | PASS
|  | 2 | Click Cancel | Triple Captain cancelled (Can only be done before activation at start of next gameweek) | Triple Captain cancelled (Can only be done before activation at start of next gameweek) | PASS
| 2.2.3 |  | Free Hit | User should be able to activate Free Hit Chip
|  | 1 | Click Free Hit | Free Hit selected and activated upon start of next gameweek | Free Hit selected and activated upon start of next gameweek | PASS
|  | 2 | Click Cancel | Free Hit cancelled (Can only be done before activation at start of next gameweek) | Free Hit cancelled (Can only be done before activation at start of next gameweek) | PASS
| 2.3 |  | Switching views | User should be able to switch between pitch view and list view
|  | 1 | Click List view | List View loaded | List View loaded | PASS
|  | 2 | Click pitch view | Pitch View loaded | Pitch View loaded | PASS
| 2.4 |  | Fixtures list | User should be able to view fixtures of upcoming gameweek and be able to switch between gameweeks
|  | 1 | Click next gameweek | Next gameweek fixtures loaded | Next gameweek fixtures loaded | PASS
|  | 2 | Click previous gameweek | Previous gameweek fixtures loaded | Previous gameweek fixtures loaded | PASS
3 |  |  | Points Page
| 3.1 |  | View points | User should be able to view points for current/most recent game week and older gameweeks also
|  | 1 | Click Points tab | Points Page loaded for current/ongoing gameweek | Points Page loaded for current/ongoing gameweek | PASS
| 3.1.1 |  | View player points | User should be able to view points of selected player for current/most recent game week and older gameweeks also
|  | 1 | Click on any player | Popup with current/ongoing gameweek points breakdown launched | Popup with current/ongoing gameweek points breakdown launched | PASS
|  | 2 | Click View Info | Player Information is displayed | Player Information is displayed | PASS
| 3.2 |  | View Dream Team | User should be able to view Dream Team of same gameweek
|  | 1 | Click Dream Team | User redirected to Dream Team of current/ongoing gameweek | User not redirected anywhere | FAIL
| 3.3 |  | Switching views | User should be able to switch between pitch view and list view
|  | 1 | Click List view | List View loaded | List View loaded | PASS
|  | 2 | Click pitch view | Pitch View loaded | Pitch View loaded | PASS
| 3.4 |  | Fixtures list | User should be able to view fixtures and results of ongoing/completed gameweek and be able to switch between gameweeks
|  | 1 | Click next gameweek | Next gameweek fixtures loaded | Next gameweek fixtures loaded | PASS
|  | 2 | Click previous gameweek | Previous gameweek fixtures loaded | Previous gameweek fixtures loaded | PASS
4 |  |  | Transfers Page
| 4.1 |  | Transfer Buttons | User should be able to access options via these buttons
|  | 1 | Choose button to click on | Said action completed upon clicking of button | Said action completed upon clicking of button | PASS
| 4.1.1 |  | Auto Pick | User should have their team autofilled based on the best permutation available
|  | 1 | Click Auto Pick button | Team autofilled based on best permutation | Team autofilled based on best permutation | PASS
| 4.1.2 |  | Reset | User should be able to undo all changes made before saving
|  | 1 | Click reset button | All unsaved changes are reset to default | All unsaved changes are reset to default | PASS
| 4.1.3 |  | Play Wildcard | User should be able to activate wildcard after making changes (one time use)
|  | 1 | Click Play Wildcard Button | Wildcard activated | Wildcard activated | PASS
| 4.1.4 |  | Make Transfers | User should be able to confirm changes made and redirect to my team page
|  | 1 | Click Make Transfers | Popup appears with list of changes made and confrimation is asked | Popup appears with list of changes made and confrimation is asked | PASS
|  | 2 | Click Confirm | Transfers confirmed and my team page loaded | Transfers not confirmed and not shown in My Team page | FAIL
| 4.2 |  | Transferring players | User should be able to choose which player to transfer out
|  | 1 | Select which player to remove and add | User can choose to add or remove players | User can choose to add or remove players | PASS
| 4.2.1 |  | Selecting player in team | User should be able to choose whether to remove or replace player or view info
|  | 1 | Click on player | Popup appears with options to remove, replace or view info | Popup appears with options to remove, replace or view info | PASS
|  | 2 | Click on remove | Player is removed and slot is now empty | Player is removed and slot is now empty | PASS
| 4.2.2 |  | Selecting empty slot in team | User should be able to choose whether to add player or restore removed player
|  | 1 | Click on empty slot | Popup appears with options to add player or restore the original player | Popup appears with options to add player or restore the original player | PASS
|  | 2 | Click on add player | Player List reloads with available players from that position | Player List reloads with available players from that position | PASS
| 4.3 |  | Player Selection from List | User should be able to select which player to add to team from the list available
|  | 1 | Click on player name | Popup appears with options to add player to team or view info | Popup appears with options to add player to team or view info | PASS
|  | 2 | Click on add player | Player added to team in any empty slot in the same position | Player added to team in any empty slot in the same position | PASS
| 4.3.1 |  | Filters | User should be able to filter list via the given options
|  | 1 | Select filters | Player List reloads and filtered list is shown | Player List reloads and filtered list is shown | PASS
| 4.3.2 |  | Selecting player name | User should be able to choose whether to add player to team or view info
|  | 1 | Click on player name | Popup appears with options to add player to team or view info | Popup appears with options to add player to team or view info | PASS
|  | 2 | Click on add player | Player added to team in any empty slot in the same position | Player added to team in any empty slot in the same position | PASS
| 4.3.3 |  | View Information | User should be able to view information of player selected
|  | 1 | Click View Information | Player information is displayed in a popup | Player information is displayed in a popup | PASS
| 4.3.4 |  | List page navigator | User should be able to navigate between pages of players list
|  | 1 | Next Page | Next page in list loaded | Next page in list loaded | PASS
|  | 2 | Previous Page | Previous page in list loaded | Previous page in list loaded | PASS
| 4.4 |  | Exceptions | User should be prompted upon performing a task against the rules
| 4.4.1 |  | Too many players of same position | User should not be allowed to add player of maxed out position and prompted the same
|  | 1 | Add player of certain position to team where all positions are filled up | Get prompt saying you can't add more than X no. of players for the selected position | Get prompt saying you can't add more than X no. of players for the selected position | PASS
| 4.4.2 |  | Too many players of same team | User should be prompted upon adding more than 3 players from the same club
|  | 1 | Add a player to team where 3 other players of same club already exist | Player added and get prompt saying you have more than 3 players of same club. Make transfers button is disabled | Player added and get prompt saying you have more than 3 players of same club. Make transfers button is disabled | PASS
| 4.4.3 |  | Budget exceeded | User should be prompted upon adding a player whose cost exceeds the players remaining budget
|  | 1 | Add a player whose price exceeds the amount left in bank | Player added; Amount in bank shows negative value in red and make transfers button is disabled | Player added; Amount in bank shows negative value in red and make transfers button is disabled | PASS
| 4.4.4 |  | Player already in team | User should not be allowed to select player that is already present in team from the list
|  | 1 | Click add player | Players already in team are disabled and cannot be added | Players already in team are disabled and cannot be added | PASS
| 4.5 |  | Switching views | User should be able to switch between pitch view and list view
|  | 1 | Click List view | List View loaded | List View loaded | PASS
|  | 2 | Click pitch view | Pitch View loaded | Pitch View loaded | PASS
| 4.6 |  | Fixtures list | User should be able to view fixtures of upcoming gameweek and be able to switch between gameweeks
|  | 1 | Click next gameweek | Next gameweek fixtures loaded | Next gameweek fixtures loaded | PASS
|  | 2 | Click previous gameweek | Previous gameweek fixtures loaded | Previous gameweek fixtures loaded | PASS
5 |  |  | Leagues Page
| 5.1 |  | New League | User should be given options to create, join or renew leagues
|  | 1 | Click create/join new league | Redirect to page with options to create new league or join new league | Redirect to page with options to create new league or join new league | PASS
| 5.2 |  | Existing League | User should be able to view their standings in all leagues they are members of
|  | 1 | Browse my leagues | Display standings in each league in which the User is a member | Display standings in each league in which the User is a member | PASS
| 5.2.1 |  | League Member | User should be able to choose whether to leave league or view standings
|  | 1 | Click on gear icon next to league with different admin | Popup appears with options to view league standings or leave the league | No popup appears | FAIL
| 5.2.2 |  | League Admin | User should be able to choose whether to view standings, invite friends or administer league
|  | 1 | Click on gear icon next to league where Admin is the User | Popup appears with options to view league standings or invite friends or administer the league | Popup appears with options to view league standings or invite friends or administer the league | PASS
| 5.3 |  | Selected League | User should be able to view expanded standings of selected league
|  | 1 | Click on league name | Redirected to new page with league standings (detailed) | Redirected to new page with league standings (detailed) | PASS
| 5.3.1 |  | View Team | User should be able to view team of other members of selected league
|  | 1 | Click on any team name in any league | Redirected to point page of selected team | Redirected to point page of User's team | PASS
| 5.3.2 |  | Filters | User should be able to filter standings by phase or month
|  | 1 | Choose filters for standings | Standings with filters applied are shown | Standings with filters applied are shown | PASS
| 5.4 |  | League Administration | User should be able to perform changes on league if they are the admin
|  | 1 | Click on administer league on the popup of gear icon next to league where User is admin | League Administration page is opened | League Administration page is opened | PASS
| 5.4.1 |  | League Code | User should be able to view or regenarate league code
|  | 1 | Click regenerate | New league code generated | New league code generated | PASS
| 5.4.2 |  | League Details | User should be able to change league name, scoring and privacy setttings
|  | 1 | Enter new details | League details changed | League details changed | PASS
| 5.4.3 |  | League Delete | User should be able to delete league
|  | 1 | Click Delete League | League Deleted | League Deleted | PASS

## Defect
Scenario Id | Sub Scenario Id | Script ID/Step | Defect ID | Defect Description | Description | Expected Result | Severity
1
| 1.1.2 |  |  |  | User Sign In | User Should be allowed to Login
|  | 1 |  |  | Click Login | User logged in and redirected to home page
|  |  | #D1010 | User not logged in | User not logged in and login page is reloaded | User logged in and redirected to home page | SHOW STOPPER
2
| 2.1.1 |  |  |  | Player in playing XI | User should be able to substitute player with player on bench(same position) or choose between making captain or vice captain or view information about the player
|  | 4 |  |  | Set Vice Captain/Vice Captain | User allowed to set one player in playing XI as captain and one as vice captain
|  |  | #D5445 | Captain/Vice Captain not changing | User unable to select captain/vice captain and save changes | User allowed to set one player in playing XI as captain and one as vice captain | HIGH
3
| 3.2 |  |  |  | View Dream Team | User should be able to view Dream Team of same gameweek
|  | 1 |  |  | Click Dream Team | User redirected to Dream Team of current/ongoing gameweek
|  |  | #D5467 | User not redirected anywhere | User not redirected to Dream Team of current/ongoing gameweek | User redirected to Dream Team of current/ongoing gameweek | LOW
4
| 4.1.4 |  |  |  | Make Transfers | User should be able to confirm changes made and redirect to my team page
|  | 2 |  |  | Click Confirm | Transfers confirmed and my team page loaded
|  |  | #D4353 | Transfers not saved | Transfers not confirmed and not shown in My Team page | Transfers confirmed and my team page loaded | CRITICAL
5
| 5.2.1 |  |  |  | League Member | User should be able to choose whether to leave league or view standings
|  | 1 |  |  | Click on gear icon next to league with different admin | Popup appears with options to view league standings or leave the league
|  |  | #D7878 | No popup appears | Popup with options to view league standings or leave the league doesn't appear | Popup appears with options to view league standings or leave the league | MEDIUM